## Slide 1
Combinatorial Test Tool
DVA313 - Group 2

## Slide 2: Basic Functionality
A tool for automatic generation of test inputs.
The software should run as a GUI tool written in C# and running on Windows.
2
XML File
XML Parser
Inputs
Data Types
Test Generation
Random
Base Choice
Show Tests
Add
Move
Remove
CSV file
Tool
Save tests

## Slide 3: Members & Roles
Adeel Khan - Document Manager, Developer Algorithm
Henning Bergström - Developer XML Parsing
Juan Antonio López Muntaner – Configuration Manager, Developer XML Parsing
Linus Eklund – Developer GUI
Meera Aravind - Project Manager, Developer Algorithm
Sara Ericsson – Developer Algorithm
Simon Eklund - Client contact, Developer GUI
3

## Slide 4: Planned Activities – Previous Week
Add/move/remove options added
Presentation – design description
Error handling and tuning the product
  Algorithms, Implementation of multiple intervals – Adeel, Meera and Sara
  Parser – Juan and Henning
  Looking into if the Parser needs to be remade to be able to handle huge files.
  GUI – Linus and Simon
  Error handling and implementing a treeview of the xml files.
4

## Slide 5: Previous Week - Outcome
Treeview for XML files almost complete
Error handling on intervals and running an “empty” program
Add/Move/Remove implemented
Implementation of multiple intervals
Presentation – design description
Outcome of test can and will no be displayed in tool

## Slide 6: Planned Activities - Next Week
Rework the parser - Juan & Henning
Work on GUI (Tree-view, error handling) - Linus & Simon
Solving floating point issue in algorithm – Sara, Meera, Adeel
Looking into the possibility to use the tool without loading an XML file – Everyone
Option to save tests as projects (optional) - Everyone

## Slide 7: Number of hours worked
Team Member | Hours worked | Accumulated hours
Adeel | 18 | 88
Henning | 19 | 88
Juan | 19 | 90
Linus | 19 | 94
Meera | 19 | 96
Sara | 19 | 93
Simon | 19 | 89
7

## Slide 8: Remaining Project Backlog
Implementation
  GUI – Error handling / completing treeview
  Reworking the XML parser
  Suggest initial values in XML files as base value
  Option to use tool without XML file loaded (optional)
  Option to save tests as projects (optional)
  Tool running as DLL callable by other applications (optional)
Project Report
Design description document (Final Version)
Final presentation
8

## Slide 9
9
THANK YOU !!!